## Hoja1
SPRINT BACKLOG | [5 empty] | SPRINT |  | DURATION |  | START
[6 empty] | 1 |  | 7 |  | 2020-06-29
REQUEST | TASK | WHO | STATE (Complete/Uninitiated/In progress | DAY | 2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-06 | 2020-07-07 | 2020-07-08
|  |  |  | Hours | 100 | 90 | 70 | 65 | 50 | 30 | 20 | 10
Request A | Refactoring of mobile app screens, Phone screen | Franchesca Man Ging | Complete |  | 2
Request A | Refactoring of mobile app screens, Orders screen | Danny Ríos | Complete |  | 2
Request A | Refactoring of mobile app screens, registration screen | Danny Ríos | Complete |  | 2
Request A | Refactoring of mobile app screens, Password change screen | Danny Ríos | Complete |  | 2
Request A | Refactoring of mobile app screens, Login screen | Danny Ríos | Complete |  | 2 | 2
Request A | Refactoring of mobile app screens, shopping cart screen | Jonathan Quintana | Complete |  |  | 2
Request A | Refactoring of mobile app screens, Home screen | Jonathan Quintana | Complete |  |  | 1
Request A | Refactoring of mobile app screens, User Profile screen | Karla Burgos | Complete |  |  | 1
Request A | Refactoring of mobile app screens, Edit Profile screen | Karla Burgos | Complete |  |  | 1
Request A | Security file refactoring in api | Jonathan Quintana | Complete |  |  | 5
Request A | Order file refactoring in api | Danny Ríos | Complete |  |  | 1
Request A | User file refactoring in api | Karla Burgos | Complete |  |  | 1
Request A | Role File refactoring in api | Karla Burgos | Complete |  |  | 1
Request A | Novelty file refactoring in api | Jonathan Quintana | Complete |  |  | 1
Request A | Login file refactoring in api | Jonathan Quintana | Complete |  |  | 1
Request A | Payment file refactoring in api | Jonathan Quintana | Complete |  |  | 1
Request A | Purchase file refactoring in api | Franchesca Man Ging | Complete |  |  | 1
Request A | Invoices file refactoring in api | Franchesca Man Ging | Complete |  |  | 1
Request B | Layout of the graphical interface of the system Login screen, registration, change of password and orders | Danny Ríos | Complete |  |  |  | 5
Request B | Graphical interface layout of the user profile screen and edit profile | Karla Burgos | Complete |  |  |  |  | 5
Request B | Graphical interface layout of the order history screen and order tracking | Franchesca Man Ging | Complete |  |  |  |  | 5
Request B | Graphic interface layout of the home screen system, product tabs and shopping cart | Jonathan Quintana | Complete |  |  |  |  | 5
Request B | Upload api to pre Production server | Danny Ríos | Complete | [5 empty] | 3
Request B | JWT refresh token settings | Danny Ríos | Complete | [5 empty] | 4
Request B | Implementation of security in the api | Danny Ríos | Complete | [5 empty] | 2.5
Request B | Access control to user data | Danny Ríos | Complete | [5 empty] | 5
Request B | JWT encryption implementation | Danny Ríos | Complete | [5 empty] | 5.5
Request B | Creation of order screens, reports and modification of menus | Brenda Bermello | In Progress
Request B | Refresh token settings in mobile app with interceptors | Franchesca Man Ging | In Progress
Request B | Mobile application login functionality | Franchesca Man Ging | In Progress
Request B | Implementation of registry to the system api | Jonathan Quintana | In Progress
Request B | Implementation of a registered cell number confirmation system. | Jonathan Quintana | In Progress
Request B | Registry implementation with firebase | Jonathan Quintana | In Progress
Request B | Implementation of guards for access control | Franchesca Man Ging | In Progress